## Sheet1
Project Name |  | OrangeHRM | Environment
Tester's Name |  | Avishek Dey Sarker | Reviewed By
Date Tested |  | 18.05.2023 | Version | 6.5.11
Issue Id | Module | Issue Title | Description | Steps to Reproduce | Issue Type | Priority | Severity | Actual Result | Expected Result | Attachment
1 | Create New Employee | user log in | Enter username and password then click on log in button.password not strong.it should be needed one special character. | 1.user name:Admin 2.password :admin123 3.click on Login button | improvement | low | low
2 | Add employee | go to pim and add employee | enter first name,middle name and last name but middle name not show in profile | 1.First name:Sabbir 2.Middle name:Hossen 3.Last name:Shovon 4.0272272 | improvement | low | low
3 |  | personal details | here for smoker issue yes options is there but no option missing | 1.smoker:yes | improvement | low | low
4 |  | contact details | for each country valid contact number is not selected | contact number:0179008030 | Bug | high | high
5 |  | Emergency contact details | for each country valid contact number is not selected but enter invalid contact then contact is included | contact number:01789272 | Bug | high | high
6 |  | immigration | for each country valid contact number is not selected,all kind of values work there but enter invalid contact then contact is included | contact number:0178abv72 | Bug | high | high
7 |  | job | job specification not defined | job specification:not defined | Bug | medium | medium
8 |  | Membership | after put one input this system works,not need all inputs | Membership:AccA | Bug | high | high
9 |  | Search | after add new employee successfully when I click on search option for searching new employee name I can't find | Search:Sabbir Hosen Shovon | Bug | high | high